Amalgamation of Abbey NS and Scoil Mhuire

Agreed Report

A meeting of the Project Management Committee for the amalgamation of Abbey National School and Scoil Mhuire was held at 4p.m., on Wednesday, January 20th in the Parochial House, Roscommon.

Decisions

It was agreed that-

- A delegation consisting of representatives from the management committee will meet with an official of the DES to discuss resources and finance before the next meeting, scheduled for March 1st, 2016.

- From the 1st September, 2017, all classes will be mixed boys and girls throughout in the new co-educational school on the two sites (Convent and Abbey).

- There will be a mix of teachers from both the Abbey NS and Convent NS in both buildings (Abbey and Convent).

- 5th and 6th classes (boys and girls) will be housed in the Abbey building starting on the 1st September, 2017.

- A uniform committee to select a uniform for the new co-educational school will be set up consisting of 6 parent representatives (3 from each school’s Parent Association) 2 teacher representatives (one from each school) and the principal from each school.